Final Project Report Mandalina Branding

Organization: YAT Learning Solutions Profile Name: Graphic Designer

Technical Instructor Name: Andrew Ibrahim Code: YAT557B_CAI3_DRT4_S4_DEPI3

Team Members:

-Alzahraa Farag (Team leader )

- Hager Ali

- Fayrouz Mahmoud

- Sawsan khaled

Table of Contents

| Section | Page |
| --- | --- |
| Project Name | 1 |
| Project Overview | 1 |
| Objectives | 1 |
| Scope | 1 |
| Task Assignment & Roles | 2 |
| Risk Assessment & Mitigation Plan | 2 |
| Key Performance Indicators (KPIs) | 3 |
| Lecturer Review | 3 |

Project Name

Mandalina Branding

Project Overview

The Mandalina Brand Identity Project focuses on creating a modern, minimal, and

emotionally driven visual identity inspired by the warmth of a grandmother’s handmade

desserts and the freshness of mandarin. The project includes developing the brand story,

logo system, color palette, typography, and social media applications, ensuring a cohesive

and memorable brand presence. The goal is to position Mandalina as a refined, heartfelt

dessert brand with a soft and timeless aesthetic.

Objectives

-To develop a cohesive and modern brand identity for Mandalina that reflects warmth, aut

henticity, and freshness. The objective is to translate the brand’s story into a minimal vis

ual system—including logo, colors, typography, and applications—to create a memorable

and emotionally engaging customer experience.

Scope

- Logo:Developing the main logo, variations, and grid system.

- Color palette (five main colors): Selecting a cohesive set of brand colors refle

cting Mandalina’s warmth and freshness.

- Typography : Defining primary(Brillant) and secondary(NEXA) typefaces and

their usage guidelines.

- Packaging mockups: Creating minimal, elegant packaging concepts aligned w

ith the brand identity.

- Social media visuals and brand templates: Designing consistent templates for

posts, stories, and brand communications.

Task Assignment & Roles

| Team Member | Defined Responsibilities (Specific Contributions) |
| --- | --- |
| Alzahraa Farag ( Team leader) | Logo sketch, P ackaging Mockups, Social Media,Assets, Presentation Visuals |
| Fayrouz Mahmoud | Logo design, Brand Story, ,packaging M ockups, social media posts |
| Hager Ali | Brand Personality, Color Palette, Social Media Guidelines , Vision & Mission |
| Sawsan Khaled | Packaging Mockups, Typography Implementation, Logo Application |

Risk Assessment & Mitigation Plan

| Milestone | Deliverable/Topic | Team Responsibility | Status |
| --- | --- | --- | --- |
| M1 | Brand Story & Core Identity (Vision, Mission, Personality) | Fayrouz Mahmoud | Completed |
| M2 | Visual Identity Foundation (Logo Inspiration, Mascot Design, Color Palette) | Fayrouz Mahmoud, Hager Ali | Completed |
| M3 | Final Design Assets (Logo Variations, Mascot, Color Palette, Typography) | Alzahraa Farag, Hager Ali, Sawsan Khaled& Fayrouz Mahmoud | Completed |
| M4 | Brand Application (Packaging Mockups, Social Media Assets) | Sawsan Khaled, Alzahraa Farag, Hager Ali& Fayrouz Mahmoud | Completed |
| M5 | Final Presentation Assets | Hager Ali& Alzahraa Farag | Completed |

Key Performance Indicators (KPIs)

| Metric | Target/Rationale |
| --- | --- |
| Brand Cohesion | Achieve consistent use of the color palette across 100% of media and mockups to maintain brand identity. |
| Typography Consistency | Ensure Brillant & NEXA are used correctly across all materials for a cohesive brand vo ice. |
| Project Completion | 100% of planned deliverables finalized and ready for submission. |
| Logo & Mascot Recognition | Ensuring the Mandalina logo is easily identifiable and memorable across all platforms by maintaining consistency in its shape, proportions, and visual style. |

Lecturer Review

- Feedback & Evaluation: Assessed visual identity, mascot, packaging, and social media mockups for consistency and brand alignment.

- Suggested Improvements: Minor adjustments on mascot scaling in some mockups; color contrast reviewed for better readability.

- Final Grading Criteria: Creativity, visual consistency, clarity of mockups, adherence to brand identity guidelines, and presentation quality.